One-Year Marketing Timetable for Community Programs

If you are doing a “community program,” this is the timetable to use to maximize registrations and marketing effectiveness. Community programs include any that reach individuals in their residences (as opposed to work place), and usually have activities (classes, events) for personal development, such as: - Community education - Recreation - Avocational and leisure learning - Noncredit The critical part is when the brochure is mailed. Mail five to seven weeks before the start of classes. Earlier than seven weeks and it is too far out for people to plan, later than five weeks and people do not have enough time to plan. Recommended Timetable for Courses 6 months out - Develop/select new courses. 5 months out - Analyze reports from last 12 months. - Set division goals: financial & registration totals, new vs. old and segments/niches. 4 months out - Finalize courses, descriptions, logistics and prices. - Prepare all other information and artwork for brochure. 3 months out - Get brochure desktopped, proofed and prepared for printer. - Get brochure printed. 7 weeks out - Do first brochure mailing. - Do first street distribution. 6 weeks out - Do any specialty brochure mailings. 5 weeks out - Do second brochure mailing. - Restock street distribution. 4 weeks out - Do radio, TV and newspaper work so advertising/publicity occurs during the two weeks prior to the start of courses. - Do any posters, speaking engagements or other segment/ niche-focused publicity/public relations. - Send out email promotion. - As registrations come in, stuff confirmation letters with announcements of some upcoming events. - Look at the half-life of courses to determine which stars you may want to spend more promotion dollars or time on. 0-3 weeks out - Send final emails. - Continue restocking street distribution. - Continue to look at half-life of courses and start making go/no-go decisions on courses. After start of courses - Analyze financial and registration totals and evaluations. - Run and analyze end-of-term reports.